## Planning Date
#VALUE! | Fertilizer Construction Project |  |  |  | Project Start |  | 2020-01-01 | time axis 2020-01-01 to 2020-05-12
[5 empty] | Current Date |  | 2020-03-23
|  |  |  | Project End |  |  | 2020-04-30
Activity ID | Activtiy Name | Duration | Predecessor | Relation-ship | Lag | Plan Start | Plan End | Actual Start | Actual End | 2020-01-01: 2020-01-01; 2020-01-08: 2020-01-08; 2020-01-15: 2020-01-15; 2020-01-22: 2020-01-22; 2020-01-29: 2020-01-29; 2020-02-05: 2020-02-05; 2020-02-12: 2020-02-12; 2020-02-19: 2020-02-19; 2020-02-26: 2020-02-26; 2020-03-04: 2020-03-04; 2020-03-11: 2020-03-11; 2020-03-18: 2020-03-18; 2020-03-25: 2020-03-25; 2020-04-01: 2020-04-01; 2020-04-08: 2020-04-08; 2020-04-15: 2020-04-15; 2020-04-22: 2020-04-22; 2020-04-29: 2020-04-29; 2020-05-06: 2020-05-06
[10 empty] | 2020-01-07 | [6 empty] | 2020-01-14 | [6 empty] | 2020-01-21 | [6 empty] | 2020-01-28 | [6 empty] | 2020-02-04 | [6 empty] | 2020-02-11 | [6 empty] | 2020-02-18 | [6 empty] | 2020-02-25 | [6 empty] | 2020-03-03 | [6 empty] | 2020-03-10 | [6 empty] | 2020-03-17 | [6 empty] | 2020-03-24 | [6 empty] | 2020-03-31 | [6 empty] | 2020-04-07 | [6 empty] | 2020-04-14 | [6 empty] | 2020-04-21 | [6 empty] | 2020-04-28 | [6 empty] | 2020-05-05 | [6 empty] | 2020-05-12
[10 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19
10 | Cleaning | 5 |  |  |  | 2020-01-01 | 2020-01-05 | 2020-01-03 | 2020-01-07 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Marking | 4 | Cleaning | FS |  | 2020-01-06 | 2020-01-09 | 2020-01-08 | 2020-01-11 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Excavation | 12 | Marking | FS |  | 2020-01-10 | 2020-01-21 | 2020-01-12 | 2020-01-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | PCC | 6 | Excavation | FS |  | 2020-01-22 | 2020-01-27 | 2020-01-24 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Footing | 12 | PCC | FS | 0 | 2020-01-28 | 2020-02-08 | 2020-01-30 | 2020-02-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | Backfilling | 4 | Footing | FS | 0 | 2020-02-09 | 2020-02-12 | 2020-02-11 | 2020-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | Plinth Beam | 12 | Backfilling | FS | 0 | 2020-02-13 | 2020-02-24 | 2020-02-15 | 2020-02-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Grade Slab | 4 | Plinth Beam | FS | 0 | 2020-02-25 | 2020-02-28 | 2020-02-27 | 2020-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Slab | 12 | Grade Slab | FS | 0 | 2020-02-29 | 2020-03-11 | 2020-03-02 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Column | 6 | Slab | FS | 0 | 2020-03-12 | 2020-03-17 | 2020-03-14 | 2020-03-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Destagging and Deshuttering | 3 | Column | FS | 0 | 2020-03-18 | 2020-03-20 | 2020-03-20 | 2020-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | Blockwork | 14 | Destagging and Deshuttering | FS | 0 | 2020-03-21 | 2020-04-03 | 2020-03-23 | 2020-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | Plaster | 7 | Blockwork | FS | 0 | 2020-04-04 | 2020-04-10 | 2020-04-06 | 2020-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | Painting | 4 | Plaster | FS | 0 | 2020-04-11 | 2020-04-14 | 2020-04-13 | 2020-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | Finishing Completion | 1 | MEP Work Completion | FS | 0 | 2020-04-18 | 2020-04-18 | 2020-04-20 | 2020-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | Site handover to Client | 1 | Finishing Completion | FS | 0 | 2020-04-19 | 2020-04-19 | 2020-04-21 | 2020-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | Mechanical Work | 4 | Plaster | FS | 0 | 2020-04-11 | 2020-04-14 | 2020-04-13 | 2020-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | Electrical Work | 7 | Plaster | FS | 0 | 2020-04-11 | 2020-04-17 | 2020-04-13 | 2020-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | Plumbing Work | 3 | Plaster | FS | 0 | 2020-04-11 | 2020-04-13 | 2020-04-13 | 2020-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | MEP Work Completion | 7 | Plaster | FS | 0 | 2020-04-11 | 2020-04-17 | 2020-04-13 | 2020-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dash Board-4 (hidden)
STATUS DATE | 2023-01-15 |  |  |  |  | PROJECT : MANAGEMENT INFORMATION SYSTEM
| TIME PERFORMANCE | [7 empty] | COST PERFORMANCE
[6 empty] | 3 Week PLANNED VS ACHIEVED | [20 empty] | 3 WEEK LOOK AHEAD
TOP 10 CRITICAL WORK (In Priority Order) | [5 empty] | 2022-12-25 | [6 empty] | 2023-01-01 | [6 empty] | 2023-01-08 | [6 empty] | 2023-01-15 | [6 empty] | 2023-01-22 | [6 empty] | 2023-01-29
 | time axis 2022-12-25 to 2023-02-04
ID | Activity Name | time axis 2022-12-25 to 2023-02-04
1 WBS | Tower -A | 2023-01-07 | 2023-01-12 | 2023-01-07 | 2023-01-13
2 | B | 2023-01-07 | 2023-01-10 | 2023-01-07 | 2023-01-11
3 | C | 2023-01-09 | 2023-01-12 | 2023-01-09 | 2023-01-13
4 WBS | Tower - D | 2023-01-13 | 2023-03-04 | 2023-01-13 | 2023-01-16
5 | E | 2023-01-13 | 2023-01-16 | 2023-01-13 | 2023-01-16
6 | F | 2023-01-15 | 2023-01-18 | 2023-01-15 | 0
7 | G | 2023-01-17 | 2023-01-20 | 0 | 0
8 | H | 2023-01-21 | 2023-01-24 | 0 | 0
9 | I | 2023-01-25 | 2023-01-28 | 0 | 0
10 | J | 2023-01-29 | 2023-02-01 | 0 | 0

## Dash Board-2B (hidden)
STATUS DATE | 2023-01-15 |  |  |  |  | PROJECT : MANAGEMENT INFORMATION SYSTEM
[6 empty] | 3 Week PLANNED VS ACHIEVED | [20 empty] | 3 WEEK LOOK AHEAD
TOP 10 CRITICAL WORK (In Priority Order) | [5 empty] | 2022-12-25 | [6 empty] | 2023-01-01 | [6 empty] | 2023-01-08 | [6 empty] | 2023-01-15 | [6 empty] | 2023-01-22 | [6 empty] | 2023-01-29
 | time axis 2022-12-25 to 2023-02-04
ID | Activity Name | time axis 2022-12-25 to 2023-02-04
1 WBS | Tower -A | 2023-01-07 | 2023-01-12 | 2023-01-07 | 2023-01-13
2 | B | 2023-01-07 | 2023-01-10 | 2023-01-07 | 2023-01-11
3 | C | 2023-01-09 | 2023-01-12 | 2023-01-09 | 2023-01-13
4 WBS | Tower - D | 2023-01-13 | 2023-03-04 | 2023-01-13 | 2023-01-16
5 | E | 2023-01-13 | 2023-01-16 | 2023-01-13 | 2023-01-16
6 | F | 2023-01-15 | 2023-01-18 | 2023-01-15 | 0
7 | G | 2023-01-17 | 2023-01-20 | 0 | 0
8 | H | 2023-01-21 | 2023-01-24 | 0 | 0
9 | I | 2023-01-25 | 2023-01-28 | 0 | 0
10 | J | 2023-01-29 | 2023-02-01 | 0 | 0

## Schedule
| PROJECT START DATE |  | 2023-01-01 |  | Uttar Pradesh Govertment
| PROJECT END DATE |  | 2023-03-04 |  | HURL Fertilizer Uttarpradesh
[12 empty] | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6
| Project Status Date |  | 2023-01-15 | [6 empty] | 154 lac | 30.8 lac | 2023-01-01 | [6 empty] | 2023-01-08 | [6 empty] | 2023-01-15 | [6 empty] | 2023-01-22 | [6 empty] | 2023-01-29 | [6 empty] | 2023-02-05
ID | Activity Name | Original Duration | Planned Start Date | Planned End Date | Percentage Completion | Actual Start | Actual Finish | Delay | Status | Budgeted Cost (in Lac) | Actual Cost(in Lac) | time axis 2023-01-01 to 2023-02-11
 | time axis 2023-01-01 to 2023-02-11
1 WBS | Tower -A | 6 | 2023-01-07 | 2023-01-12 | 77.14% | 2023-01-07 | 2023-01-13 | 0 | WIP | 14 | 10.8
2 | B | 4 | 2023-01-07 | 2023-01-10 | 100% | 2023-01-07 | 2023-01-11 |  | Completed | 14 | 12.8
3 | C | 4 | 2023-01-09 | 2023-01-12 | 100% | 2023-01-09 | 2023-01-13 |  | Completed | 14 | 7.2
4 WBS | Tower - D | 51 | 2023-01-13 | 2023-03-04 | 0% | 2023-01-13 | 2023-01-16 |  | Not Started | 14 | 0
5 | E | 4 | 2023-01-13 | 2023-01-16 | 100% | 2023-01-13 | 2023-01-16 |  | Completed | 14 | 0
6 | F | 4 | 2023-01-15 | 2023-01-18 | 25% | 2023-01-15 |  |  | WIP | 14 | 0
7 | G | 4 | 2023-01-17 | 2023-01-20 | 0% |  |  |  | Not Started | 14 | 0
8 | H | 4 | 2023-01-21 | 2023-01-24 | 0% |  |  |  | Not Started | 14 | 0
9 | I | 4 | 2023-01-25 | 2023-01-28 | 0% |  |  |  | Not Started | 14 | 0
10 | J | 4 | 2023-01-29 | 2023-02-01 | 0% |  |  |  | Not Started | 14 | 0
11 | K | 31 | 2023-02-02 | 2023-03-04 | 0% |  |  |  | Not Started | 14 | 0
Formulas:
W1 = +[W1, row below]
W2 = +[W2, row below]
W3 = +[W3, row below]
W4 = +[W4, row below]
W5 = +[W5, row below]
W6 = +[W6, row below]

## Gantt Chart (hidden)
PROJECT TITLE
ORGANIZATION NAME
PROJECT START DATE |  | 2021-01-01
Project Status Date |  | 2021-01-15 | [6 empty] | 2021-01-01 | [6 empty] | 2021-01-08 | [6 empty] | 2021-01-15 | [6 empty] | 2021-01-22 | [6 empty] | 2021-01-29 | [6 empty] | 2021-02-05
Activity Name | Original Duration | Planned Start Date | Planned End Date | Percentage Completion | Actual Start | Actual Finish | Delay | Status | time axis 2021-01-01 to 2021-02-11
 | time axis 2021-01-01 to 2021-02-11
A | 4 | 2021-01-05 | 2021-01-08 | 100% | 2021-01-05 | 2021-01-10 | 2 | Completed
B | 4 | 2021-01-09 | 2021-01-12 | 100% | 2021-01-09 | 2021-01-12 |  | Completed
C | 4 | 2021-01-13 | 2021-01-16 | 25% | 2021-01-13 | 2021-01-13 18:00 |  | WIP
D | 4 | 2021-01-17 | 2021-01-20 | 50% | 2021-01-17 | 2021-01-23 12:00 | 5 | WIP
E | 4 | 2021-01-21 | 2021-01-24 |  |  |  |  | Not Started
F | 4 | 2021-01-25 | 2021-01-28 |  |  |  |  | Not Started
G | 4 | 2021-01-29 | 2021-02-01 |  |  |  |  | Not Started
H | 4 | 2021-02-02 | 2021-02-05 |  |  |  |  | Not Started
I | 4 | 2021-02-06 | 2021-02-09 |  |  |  |  | Not Started
J | 4 | 2021-02-10 | 2021-02-13 |  |  |  |  | Not Started
K | 4 | 2021-02-14 | 2021-02-17 |  |  |  |  | Not Started
Not Started

## Resource
Project Resource
S.no | Category | Resource Name | UOM | Rate(Rs) | Max Unit
1 | LABOR | Labor | Mandays | 1000 | 100
2 | MATERIAL | material | Numbers | 10000 | 1000
3 | MACHINE | machine | Numbers | 100000 | 2

## $ (hidden)
HOW $ WORKS IN EXCEL
|  | Sale(numbers) | [6 empty] | COST (RS)= SALE * RATE
ITEM | Rate(RS) | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07
A | 1 | 1 | 5 | 4 | 6 | 4 | 4 | 4 | 1 | 5 | 4 | 6 | 4 | 4 | 4
B | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 8 | 10 | 10
C | 3 | 4 | 6 | 4 | 4 | 4 | 4 | 4 | 12 | 18 | 12 | 12 | 12 | 12 | 12
D | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 25 | 20 | 20 | 20 | 20 | 20 | 20

## AND (hidden)
HOW AND WORKS IN EXCEL
TO BUY ITEM RATE LESS THEN Rs35 AND Profit more then Rs1
| ITEM | Rate(Rs) | Profit(Rs) |  | BUY OR NOT TO BUY
| A | 10 | 1 | NO | FALSE
| B | 20 | 2 | YES | TRUE
| C | 30 | 3 | YES | TRUE
| D | 40 | 4 | NO | FALSE

## CONDITIONAL FORMATTING (hidden)
HOW CONDITIONAL FORMATTING WORKS IN EXCEL
TO BUY ITEM RATE LESS THEN Rs35 AND Profit more then Rs1
| ITEM | Rate(Rs) | Profit(Rs) | BUY OR NOT TO BUY
| A | 10 | 1 | FALSE
| B | 20 | 2 | TRUE
| C | 30 | 3 | TRUE
| D | 40 | 4 | FALSE

## Assign Resource
PROJECT TITLE
Resource Plan
PROJECT START DATE |  | 2021-01-01
[9 empty] | Date | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | Date | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19
[9 empty] | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 41.6667 | 66.6667 | 66.6667 | 41.6667 | 41.6667 | 26.9608 | 26.9608 | 51.9608 | 51.9608 | 51.9608 | 51.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | Labor (Numbers) | 0 | 41.6667 | 51.9608 | 26.9608 | 26.9608 | 5.1866 | 0 | 0
[9 empty] | material | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 20.8333 | 33.3333 | 33.3333 | 20.8333 | 20.8333 | 13.4804 | 13.4804 | 25.9804 | 25.9804 | 25.9804 | 25.9804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | material ( Unit) | 0 | 20.8333 | 25.9804 | 13.4804 | 13.4804 | 0.98039 | 0 | 0
[9 empty] | machine | 0 | 0 | 0 | 0 | 0 | 0 | 3.3333 | 3.3333 | 5.3333 | 5.4 | 3.4 | 3.4 | 2.2 | 2.2 | 4.2 | 4.2 | 4.2 | 4.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | machine (Nos) | 0 | 3.3333 | 4.2 | 2.2 | 2.2 | 0.2 | 0 | 0
Project Status Date |  | 2023-01-15 | [7 empty] | 2023-01-01 | [6 empty] | 2023-01-08 | [6 empty] | 2023-01-15 | [6 empty] | 2023-01-22 | [6 empty] | 2023-01-29 | [6 empty] | 2023-02-05
Activity Name | Original Duration | Planned Start Date | Planned End Date | Resource | Budgeted Unit | Actual Unit | Rate | budgeted cost | Actual Cost | time axis 2023-01-01 to 2023-02-11
 | time axis 2023-01-01 to 2023-02-11
Tower -A | 6 | 2023-01-07 | 2023-01-12 | Labor | 100 | 30 | 1000 | 1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower -A | 6 | 2023-01-07 | 2023-01-12 | material | 50 | 75 | 10000 | 5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower -A | 6 | 2023-01-07 | 2023-01-12 | machine | 8 | 3 | 100000 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2023-01-07 | 2023-01-10 | Labor | 100 | 30 | 1000 | 1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2023-01-07 | 2023-01-10 | material | 50 | 75 | 10000 | 5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2023-01-07 | 2023-01-10 | machine | 8 | 5 | 100000 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 2023-01-09 | 2023-01-12 | Labor | 100 | 0 | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 2023-01-09 | 2023-01-12 | material | 50 | 0 | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 2023-01-09 | 2023-01-12 | machine | 8 | 0 | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower - D | 51 | 2023-01-13 | 2023-03-04 | Labor | 100 | 0 | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608 | 1.9608
Tower - D | 51 | 2023-01-13 | 2023-03-04 | material | 50 | 0 | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039
Tower - D | 51 | 2023-01-13 | 2023-03-04 | machine | 8 | 0 | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686 | 0.15686
E | 4 | 2023-01-13 | 2023-01-16 | Labor | 100 | 0 | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 4 | 2023-01-13 | 2023-01-16 | material | 50 | 0 | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 4 | 2023-01-13 | 2023-01-16 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 4 | 2023-01-15 | 2023-01-18 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 4 | 2023-01-15 | 2023-01-18 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 4 | 2023-01-15 | 2023-01-18 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 4 | 2023-01-17 | 2023-01-20 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 4 | 2023-01-17 | 2023-01-20 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 4 | 2023-01-17 | 2023-01-20 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 4 | 2023-01-21 | 2023-01-24 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 4 | 2023-01-21 | 2023-01-24 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 4 | 2023-01-21 | 2023-01-24 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 4 | 2023-01-25 | 2023-01-28 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 4 | 2023-01-25 | 2023-01-28 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 4 | 2023-01-25 | 2023-01-28 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 4 | 2023-01-29 | 2023-02-01 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 4 | 2023-01-29 | 2023-02-01 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 4 | 2023-01-29 | 2023-02-01 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
K | 31 | 2023-02-02 | 2023-03-04 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2258 | 3.2258 | 3.2258 | 3.2258 | 3.2258 | 3.2258 | 3.2258 | 3.2258 | 3.2258 | 3.2258
K | 31 | 2023-02-02 | 2023-03-04 | material | 50 |  | 10000 | 5 | 0
K | 31 | 2023-02-02 | 2023-03-04 | machine | 8 |  | 100000 | 8 | 0

## DPR
DAILY PROGRESS REPORT
S.no | Progress Date | Activity Name | Resource | Actual unit Consumed | Manager | UOM | Rate | Cost
1 | 2023-01-05 | Tower -A | Labor | 10 | Mr.X | Mandays | 1000 | 10000
2 | 2023-01-05 | Tower -A | material | 25 | Mr.X | Numbers | 10000 | 250000
3 | 2023-01-05 | Tower -A | machine | 1 | Mr.X | Numbers | 100000 | 100000
1 | 2023-01-06 | Tower -A | Labor | 10 | Mr.X | Mandays | 1000 | 10000
2 | 2023-01-06 | Tower -A | material | 25 | Mr.X | Numbers | 10000 | 250000
3 | 2023-01-06 | Tower -A | machine | 1 | Mr.X | Numbers | 100000 | 100000
1 | 2023-01-07 | Tower -A | Labor | 10 | Mr. Y | Mandays | 1000 | 10000
2 | 2023-01-07 | Tower -A | material | 25 | Mr. Y | Numbers | 10000 | 250000
3 | 2023-01-07 | Tower -A | machine | 1 | Mr. Y | Numbers | 100000 | 100000
1 | 2023-01-07 | B | Labor | 10 | Mr. Y | Mandays | 1000 | 10000
2 | 2023-01-07 | B | material | 25 | Mr. Y | Numbers | 10000 | 250000
3 | 2023-01-07 | B | machine | 1 | Mr. Y | Numbers | 100000 | 100000
1 | 2023-01-07 | B | Labor | 10 | Mr. Y | Mandays | 1000 | 10000
2 | 2023-01-07 | B | material | 25 | Mr. Y | Numbers | 10000 | 250000
3 | 2023-01-07 | B | machine | 3 | Mr. Y | Numbers | 100000 | 300000
1 | 2023-01-07 | B | Labor | 10 | Mr. Y | Mandays | 1000 | 10000
2 | 2023-01-07 | B | material | 25 | Mr. Y | Numbers | 10000 | 250000
3 | 2023-01-07 | B | machine | 1 | Mr. Y | Numbers | 100000 | 100000
1 | 2023-01-07 | C | Labor | 10 | Mr. Y | Mandays | 1000 | 10000
2 | 2023-01-07 | C | material | 25 | Mr. Y | Numbers | 10000 | 250000
3 | 2023-01-07 | C | machine | 1 | Mr. Y | Numbers | 100000 | 100000
1 | 2023-01-07 | C | Labor | 10 | Mr. Y | Mandays | 1000 | 10000
2 | 2023-01-07 | C | material | 25 | Mr. Y | Numbers | 10000 | 250000
3 | 2023-01-07 | C | machine | 1 | Mr. Y | Numbers | 100000 | 100000
Formulas:
Progress Date = +[Progress Date, row above]

## Graph
PROJECT START DATE | 2023-01-01
PROJECT END DATE | 2023-03-04
Project Status Date | 2023-01-15
Total Time |  | 100% |  | 62
Elapsed |  | 30.65% | 69.35% | 19
43
Total Cost |  | 100% |  | 140
incured |  | 22% | 78% | 30.8
109.2

## Planned Vs Achieved (hidden)
| Date: | 2023-01-15
|  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Resources | Planned till Date | Achieved Till Date | time axis 2023-01-01 to 2023-03-15
2 | Labor | 353.9216 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 41.6667 | 66.6667 | 66.6667 | 41.6667 | 41.6667 | 26.9608 | 26.9608 | 51.9608 | 51.9608 | 51.9608 | 51.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 26.9608 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | 5.1866 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | material | 176.9608 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 20.8333 | 33.3333 | 33.3333 | 20.8333 | 20.8333 | 13.4804 | 13.4804 | 25.9804 | 25.9804 | 25.9804 | 25.9804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 13.4804 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | 0.98039 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | machine | 28.6 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3333 | 3.3333 | 5.3333 | 5.4 | 3.4 | 3.4 | 2.2 | 2.2 | 4.2 | 4.2 | 4.2 | 4.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 49.8353 | 2023-01-01: 30.8
| Resources | Rate | Planned | 2023-01-01: Achieved
| Labor | 1000 | 3.5392 | 2023-01-01: 0.8
| material | 10000 | 17.6961 | 2023-01-01: 20
| machine | 100000 | 28.6 | 2023-01-01: 10

## Sheet1
Project Total Time | 62
Project Total Elasped | 14
Project Total Cost | 154 lac | 154
Project Cost Incured | 30.8 lac | 30.8
s
| Elaped | Balance
Time Performance | 22.58% | 77.42%
Cost Performance | 20% | 80%

## Assign Resource New
PROJECT TITLE
Resource Plan
PROJECT START DATE |  | 2021-01-01
[9 empty] | Date | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | Date | 2021-01-01 | 2021-01-08 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-12 | 2021-02-19 | budgeted cost | 154 | Resources | Labor | material | machine
[9 empty] | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Actual Cost | 23.6 | Budgeted Unit | 1100 | 550 | 88
[9 empty] | material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | material | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Actual Unit | 60 | 150 | 8
[9 empty] | machine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | machine | 0 | 0 | 0 | 0 | 0 | 0
Project Status Date |  | 2021-01-15 | [7 empty] | 2021-01-01 | [6 empty] | 2021-01-08 | [6 empty] | 2021-01-15 | [6 empty] | 2021-01-22 | [6 empty] | 2021-01-29 | [6 empty] | 2021-02-05
Activity Name | Original Duration | Planned Start Date | Planned End Date | Resource | Budgeted Unit | Actual Unit | Rate | budgeted cost | Actual Cost | time axis 2021-01-01 to 2021-02-11
Original Duration | time axis 2021-01-01 to 2021-02-11
Tower -A | 6 | 2023-01-07 | 2023-01-12 | Labor | 100 | 30 | 1000 | 1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower -A | 6 | 2023-01-07 | 2023-01-12 | material | 50 | 75 | 10000 | 5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower -A | 6 | 2023-01-07 | 2023-01-12 | machine | 8 | 3 | 100000 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2023-01-07 | 2023-01-10 | Labor | 100 | 30 | 1000 | 1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2023-01-07 | 2023-01-10 | material | 50 | 75 | 10000 | 5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2023-01-07 | 2023-01-10 | machine | 8 | 5 | 100000 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 2023-01-09 | 2023-01-12 | Labor | 100 | 0 | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 2023-01-09 | 2023-01-12 | material | 50 | 0 | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 2023-01-09 | 2023-01-12 | machine | 8 | 0 | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower - D | 51 | 2023-01-13 | 2023-03-04 | Labor | 100 | 0 | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower - D | 51 | 2023-01-13 | 2023-03-04 | material | 50 | 0 | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tower - D | 51 | 2023-01-13 | 2023-03-04 | machine | 8 | 0 | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 4 | 2023-01-13 | 2023-01-16 | Labor | 100 | 0 | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 4 | 2023-01-13 | 2023-01-16 | material | 50 | 0 | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 4 | 2023-01-13 | 2023-01-16 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 4 | 2023-01-15 | 2023-01-18 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 4 | 2023-01-15 | 2023-01-18 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 4 | 2023-01-15 | 2023-01-18 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 4 | 2023-01-17 | 2023-01-20 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 4 | 2023-01-17 | 2023-01-20 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 4 | 2023-01-17 | 2023-01-20 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 4 | 2023-01-21 | 2023-01-24 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 4 | 2023-01-21 | 2023-01-24 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 4 | 2023-01-21 | 2023-01-24 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 4 | 2023-01-25 | 2023-01-28 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 4 | 2023-01-25 | 2023-01-28 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 4 | 2023-01-25 | 2023-01-28 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 4 | 2023-01-29 | 2023-02-01 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 4 | 2023-01-29 | 2023-02-01 | material | 50 |  | 10000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 4 | 2023-01-29 | 2023-02-01 | machine | 8 |  | 100000 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
K | 31 | 2023-02-02 | 2023-03-04 | Labor | 100 |  | 1000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
K | 31 | 2023-02-02 | 2023-03-04 | material | 50 |  | 10000 | 5 | 0
K | 31 | 2023-02-02 | 2023-03-04 | machine | 8 |  | 100000 | 8 | 0